## LOE Calculator
Category | Count | Hours per Unit | Total Hours | Comments | Phase | Type
Discovery - Review AD assessments | 1 | 6 | 6 | Review existing AD assessments and inventories. | Discovery & Validation | Base
Discovery - Validate trusts/DNS/object readiness | 1 | 6 | 6 | Validate trusts, DNS, and object readiness across domains. | Discovery & Validation | Base
Discovery - Trust remediation (if missing) | 0 | 2 | 0 | All required trusts present | Discovery & Validation | Risk
Discovery - Add target DC(s) if needed | 1 | 6 | 6 | Target DC count=1; baseline minimum=2 | Discovery & Validation | Risk
Design - Validate target OU readiness | 1 | 4 | 4 | Validate poc.local OU structure, delegation, and placement for migrated objects. | Design & Planning | Base
Design - GPO planning (review source GPOs; create new as needed) | 15 | 0.2 | 3 | GPOs not migrated; review source GPO inventory to create required equivalents in target. | Design & Planning | Variable
Design - User naming conflicts remediation planning | 64 | 0.1 | 6.4 | User conflicts (excluded built-ins) drive mapping/rename decisions and communications. | Design & Planning | Risk
Design - Group naming conflicts remediation planning | 5 | 0.1 | 0.5 | Group name collisions: reuse existing target groups if possible; rename migrated groups as needed. | Design & Planning | Risk
Design - Computer naming conflicts remediation planning | 4 | 0.1 | 0.4 | Computer name collisions: pre-rename or migration rename mapping. | Design & Planning | Risk
Migration - User migrations (source domains) | 129 | 0.15 | 19.35 | Enabled users in source domains to migrate. | Migration Execution | Variable
Migration - Group migrations (source domains) | 168 | 0.05 | 8.4 | Groups in source domains to migrate as needed (reuse target where possible). | Migration Execution | Variable
Migration - Workstation migrations (active; source domains) | 40 | 0.25 | 10 | Active workstations in source domains to migrate. | Migration Execution | Variable
Migration - Server migrations (identity-only; source domains) | 9 | 0.1 | 0.9 | Servers in source domains (identity-only unless otherwise scoped). | Migration Execution | Variable
Post - Access validation & remediation | 169 | 0.05 | 8.45 | Validate user logon + resource access; remediation buffer. | Post-Migration | Variable
Post - Legacy domain decommissioning support | 2 | 2 | 4 | Decommissioning support per legacy source domain (optional scope item). | Post-Migration | Base
|  | Total Hours | 83.4

## LOE by Phase
LOE by Phase (SOW-Aligned)
Phase | Base Hours | Variable Hours | Risk Adders | Total Hours | Notes / Drivers
Discovery & Validation | 8 | 0 | 6 | 14 | Derived from LOE Calculator (Phase + Type) to avoid mismatches
Design & Planning | 8 | 3 | 7.3 | 18.3 | Update counts in LOE Calculator; phases update automatically
Migration Execution | 0 | 38.65 | 0 | 38.65 | User/group/device migrations; pilot + waves
Post-Migration | 4 | 8.45 | 0 | 12.45 | Access validation; issue remediation; legacy domain decommissioning support
TOTAL | 20 | 50.1 | 13.3 | 83.4
Pricing
T&M Rate ($/hr) | 0
Fixed Fee Multiplier | 1.15
T&M Estimated Cost | 0
Fixed Fee Price | 0

## Executive Summary
Executive LOE Summary (for SOW)
Project / Customer | TBD
Target Domain | POC (poc.local)
Source Domains | LIGHTHOUSE (lighthouseoptics.local), ROSSOPTICALINDU (rossoptical.local)
Report Date | 2026-01-09
Environment Snapshot |  |  | LOE Summary
Metric | Value |  | Phase | Hours
Enabled Users | 233 |  | Discovery & Validation | 14
Active Workstations | 120 |  | Design & Planning | 18.3
Servers | 13 |  | Migration Execution | 38.65
Total Groups | 320 |  | Post-Migration | 12.45
Target DCs | 1 |  | TOTAL | 83.4
Additional DCs Needed | 1
Missing Trusts (count) | 0 |  | Estimated Pricing
User Conflicts | 64 |  | T&M Rate ($/hr) | 0
Group Conflicts | 5 |  | T&M Estimated Cost | 0
Computer Conflicts | 4 |  | Fixed Fee Multiplier | 1.15
Conflict Adder Hours | 7.3 |  | Fixed Fee Price | 0
Environment Snapshot (by Domain)
Prefix | Domain | Enabled Users | Active Workstations | Servers | Groups | DCs | GPOs | Role
LIGHTHOUSE | lighthouseoptics.local | 86 | 18 | 3 | 112 | 1 | 9 | Source
POC | poc.local | 104 | 80 | 4 | 152 | 1 | 4 | Target
ROSSOPTICALINDU | rossoptical.local | 43 | 22 | 6 | 56 | 1 | 6 | Source
TOTAL |  | 233 | 120 | 13 | 320
Key Assumptions / Notes
• Target domain exists; UPN suffix standardized in target. • GPO approach: create new GPOs as needed (inventory used for planning). • Trusts must exist prior to migration (flagged if missing). • Naming conflicts add remediation effort.

## Infra & Readiness
Prefix | DomainFqdn | IsTarget | DCCount | MeetsMinTargetDCs | AdditionalDCsNeeded | SourceGPOCount | TargetHasTrustToDomain | Notes
LIGHTHOUSE | lighthouseoptics.local | FALSE | 1 |  |  | 9 | TRUE | Trust exists to target.
POC | poc.local | TRUE | 1 | FALSE | 1 | 4 |  | Recommend adding 1 DC(s) to meet baseline resiliency.
ROSSOPTICALINDU | rossoptical.local | FALSE | 1 |  |  | 6 | TRUE | Trust exists to target.

## Name Conflicts
Name Conflicts (Source â†’ Target)
Target: | POC (poc.local)
Generated: | 2026-01-13 16:34:17
Summary: | Detected 64 user naming conflicts; Detected 5 group naming conflicts; Detected 4 computer naming conflicts; add ~7.3 hrs for conflict remediation/communication.
User Conflicts (sAMAccountName and/or UPN local-part)
SourcePrefix | SourceDomain | ConflictType | sAMAccountName | UserPrincipalName | RecommendedAction
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | ConferenceRoom | ConferenceRoom@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | mskelton | mskelton@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | dbennis | dbennis@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | wdionne | wdionne@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | KClifford | KClifford@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | ahowell | ahowell@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | jlenentine | jlenentine@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | djacques | djacques@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | tmoore | tmoore@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | hhodges | hhodges@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | 1ntAdmin | 1ntAdmin@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | dchambers | dchambers@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | dlauze | dlauze@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | dpappalardo | dpappalardo@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | ksansonetti | ksansonetti@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | jhargraves | jhargraves@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | mlawande | mlawande@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | shaines | shaines@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | jeverett | jeverett@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | mspadmin | mspadmin@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | LiongardAgent | LiongardAgent@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | jmigacz | jmigacz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | bcapotosto | bcapotosto@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | ksimeone | ksimeone@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | khealy | khealy@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | pcesaitis | pcesaitis@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | mcafferty | mcafferty@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | EGengler | EGengler@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | jforkey | jforkey@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | shallinan | shallinan@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | snguyen | snguyen@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | dgillis | dgillis@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | bmartowska | bmartowska@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | kcollins | kcollins@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | bnicholson | bnicholson@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | TDlugasz | TDlugasz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | sihallinan | sihallinan@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | csorel_zz | csorel_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | hmurray_zz | hmurray_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | dthomas_zz | dthomas_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | scarter | scarter@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | csheehan_zz | csheehan_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | jmar_zz | jmar_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | econtreras_zz | econtreras_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | hweinman_zz | hweinman_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | BatmanUser | BatmanUser@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | vmello_zz | vmello_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | zjohns_zz | zjohns_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | hboal_zz | hboal_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
LIGHTHOUSE | lighthouseoptics.local | sAMAccountName + UPN local-part | plagana_zz | plagana_zz@lighthouseoptics.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | 1ntadmin | 1ntadmin@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | mspadmin | mspadmin@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | LiongardAgent | LiongardAgent@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | csorel_zz | csorel_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | dthomas_zz | dthomas_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | hmurray_zz | hmurray_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | csheehan_zz | csheehan_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | jmar_zz | jmar_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | econtreras_zz | econtreras_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | hweinman_zz | hweinman_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | vmello_zz | vmello_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | zjohns_zz | zjohns_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | hboal_zz | hboal_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
ROSSOPTICALINDU | rossoptical.local | sAMAccountName + UPN local-part | plagana_zz | plagana_zz@rossoptical.local | Rename or map to existing target identity; confirm with business owner
Group Conflicts (name collisions)
SourcePrefix | SourceDomain | GroupName | RecommendedAction
LIGHTHOUSE | lighthouseoptics.local | Sales | Reuse existing target group if equivalent; otherwise rename migrated group
LIGHTHOUSE | lighthouseoptics.local | Purchasing | Reuse existing target group if equivalent; otherwise rename migrated group
LIGHTHOUSE | lighthouseoptics.local | Shipping | Reuse existing target group if equivalent; otherwise rename migrated group
LIGHTHOUSE | lighthouseoptics.local | SSLVPN | Reuse existing target group if equivalent; otherwise rename migrated group
LIGHTHOUSE | lighthouseoptics.local | EPDM Users | Reuse existing target group if equivalent; otherwise rename migrated group
Computer Conflicts (name collisions)
SourcePrefix | SourceDomain | ComputerName | RecommendedAction
LIGHTHOUSE | lighthouseoptics.local | POC-LT-42 | Rename device prior to domain move or apply migration rename mapping
LIGHTHOUSE | lighthouseoptics.local | POC-DERVISH-01 | Rename device prior to domain move or apply migration rename mapping
LIGHTHOUSE | lighthouseoptics.local | POC-LT-24 | Rename device prior to domain move or apply migration rename mapping
LIGHTHOUSE | lighthouseoptics.local | POC-DERVISH-04 | Rename device prior to domain move or apply migration rename mapping

## Assumptions
LOE Assumptions (generated by automation)
Generated: | 2026-01-13 16:34:17
Audit CSV: | C:\Users\paull\OneDrive - Lagana Consulting\scripts\LOE calculator\outputs\PrecisionOptics_AD_Migration_LOE_Audit_20260113_163416.csv
- Target domain is existing (poc.local). Name collisions expected; UPN suffix standardized (@poc.local).
- Target DC baseline: minimum 2 DCs. Target currently reports 1 DC(s).
- GPO strategy: do not migrate GPOs; create new GPOs as required. Source GPO inventory used for planning only.
- Trust readiness: trusts should exist between target and each source domain before ADMT-style migrations.
- Users count = enabled users. Active workstations = enabled non-server OS with Logon within 30 days of ReportDate (2026-01-09).
- Servers = computers where OperatingSystem contains 'Server' (identity-only unless otherwise scoped).
- Naming conflicts are derived from sourceâ†’target comparisons: user sAMAccountName + UPN local-part; group and computer names.
- Conflict remediation LOE adders: user=0.1h, group=0.1h, computer=0.1h. Current add=~7.3h.
- Audit CSV is generated each run for traceability.